## table2.csv
| Task | Method | Date | Consultancy Days | Salary cost ($) | Expenses cost ($)
1 | Management | Two face to face meetings of the PIs and advisory group; tri-weekly video-conference planning meetings | 01/15; 05/15 | 0 | 0 | 12
2 | Definition of the prescriptive subset in TEI ODD | Workshop sprint (5 days, Mueller, Rahtz, Pytlig Zillig, Cummings, Geyken, Glorieux, Burnard); local and travel expenses | 2014-09-01 | 10 | 3600 | 10500
3 | Extension to the TEI ODD language to support processing expectations | Workshop (3 days, Rahtz, Tuurska, 4 community members); local and travel expenses | 2014-10-01 |  | 0 | 15000
4 | Definition of processing expectations for TEI Simple | Workshop sprint (Rahtz, Pytlig Zillig, Tuurska; 3 consultants); local and travel expenses | 2015-11-01 | 15 | 5400
5 | Implementation of processing expectations | Workshop sprint (5 days, Pytlig Zillig, Rahtz, contractors); local and travel expenses | 2015-12-01 | 10 | 3600 | 10500
6 | Maintainable open access documentation for TEI Simple | Mueller, contractors | 2015-02-01 | 5 | 1800
7 | Mapping TEI Simple to other ontologies | Rahtz, contractors | 2015-03-01 | 10 | 3600
8 | Development of a markup system for recording the formal profile of a text | Mueller, Pytlig Zillig, Glorieux, contractors | 2015-02-01 | 15 | 5400
9 | Implementation of profile reporting | Geyken, contractors | 2015-04-01 | 10 | 3600
10 | Integration of TEI Simple into the Guidelines and other TEI Consortium infrastructure | Rahtz, Burnard, Cummings | 2015-05-01 | 5 | 1800
11 | User validation | Open workshop at midpoint of project (2 days, local expenses only) | 2015-01-01 |  |  | 5000
| Contingency |  |  |  |  | 5000
| Total budget |  |  | 80 | 28800 | 46012 | 74812